## Sheet1
Task Mode | WBS | Task Name | Duration | Start | Finish | Predecessors
Manually Scheduled | - | Fake News Detection | 65 days | Mon 01/02/21 | Fri 30/04/21
Manually Scheduled | 1 | Planning | 8 days | Mon 01/02/21 | Wed 10/02/21
Manually Scheduled | 1.1 | Develop Project Charter | 3 days | Mon 01/02/21 | Wed 03/02/21
Manually Scheduled | 1.2 | Define System Approach and Measurement | 5 days | Tue 02/02/21 | Mon 08/02/21
Manually Scheduled | 1.3 | Identify Data Source | 5 days | Thu 04/02/21 | Wed 10/02/21
Auto Scheduled | 1.4 | Milestone 1 | 0 days | Wed 10/02/21 | Wed 10/02/21
Manually Scheduled | 2 | Design | 18 days | Mon 15/02/21 | Wed 10/03/21
Manually Scheduled | 2.1 | Data Management | 12 days | Mon 15/02/21 | Tue 02/03/21 | 5SS
Manually Scheduled | 2.1.1 | Web Scraping | 5 days | Mon 15/02/21 | Fri 19/02/21
Manually Scheduled | 2.1.2 | Data Wrangling | 6 days | Mon 15/02/21 | Mon 22/02/21
Manually Scheduled | 2.1.3 | Data Preparation | 6 days | Tue 23/02/21 | Tue 02/03/21
Manually Scheduled | 2.2 | Exploratory Data Analysis | 6 days | Wed 03/03/21 | Wed 10/03/21 | 10SS
Auto Scheduled | 2.3 | Milestone 2 | 0 days | Wed 10/03/21 | Wed 10/03/21
Manually Scheduled | 3 | Development | 13 days | Fri 12/03/21 | Tue 30/03/21
Manually Scheduled | 3.1 | Modelling | 13 days | Fri 12/03/21 | Tue 30/03/21
Manually Scheduled | 3.1.1 | Build Models | 5 days | Fri 12/03/21 | Thu 18/03/21 | 11
Manually Scheduled | 3.1.2 | Train Data | 4 days | Fri 19/03/21 | Wed 24/03/21 | 8,16
Manually Scheduled | 3.1.3 | Test Data | 4 days | Thu 25/03/21 | Tue 30/03/21 | 17
Manually Scheduled | 3.2 | Analyze Data Trend | 4 days | Thu 25/03/21 | Tue 30/03/21
Auto Scheduled | 3.3 | Milestone 3 | 0 days | Tue 30/03/21 | Tue 30/03/21
Manually Scheduled | 4 | Testing | 13 days | Mon 05/04/21 | Wed 21/04/21
Manually Scheduled | 4.1 | Test Accuracy of Data | 3 days | Mon 05/04/21 | Wed 07/04/21 | 18FS+1 day
Manually Scheduled | 4.2 | Inferences and Interpretations of Results | 6 days | Thu 08/04/21 | Thu 15/04/21
Manually Scheduled | 4.2.1 | Analyze results | 6 days | Thu 08/04/21 | Thu 15/04/21 | 22SS
Manually Scheduled | 4.3 | Debug and Correction | 4 days | Fri 16/04/21 | Wed 21/04/21 | 22
Auto Scheduled | 4.4 | Milestone 4 | 0 days | Wed 21/04/21 | Wed 21/04/21
Manually Scheduled | 5 | Implementation | 6 days? | Fri 23/04/21 | Fri 30/04/21
Manually Scheduled | 5.1 | Deploy System | 5 days | Fri 23/04/21 | Thu 29/04/21 | 25FF
Manually Scheduled | 5.2 | Documentation | 5 days | Mon 26/04/21 | Fri 30/04/21
Auto Scheduled | 5.3 | Summary & Presentation | 3 days | Wed 28/04/21 | Fri 30/04/21